## Dashboard
NutriBite Project Tracking Dashboard
MERN + FastAPI Pediatric Nutrition Platform - Status Registry
Total Features | Completed Features | In Progress Features | Open Features | Blocked Features | Overall Completion %
Project Completion Progress Indicator
STATUS DISTRIBUTION DATA |  |  | FEATURES STATUS DISTRIBUTION CHART
Status | Count
Completed
In Progress
Review
Blocked
Open
Total Features
PROJECT HEALTH & TIMELINE SUMMARY
Project Status: | ACTIVE (Phase 5 - AI & Telemetry Integration)
Current Health: | HEALTHY (All core user workflows verified)
Target Deadline: | June 25, 2026 (Final Review)
Risks/Blockers: | None. Final RAG benchmark tests are complete.

## Features
NutriBite Feature Registry
Feature ID | Feature Name | Description | Owner | Status | Priority | Completion % | Comments
F-01 | Landing Page | Landing page explaining NutriBite's clinical and gamified modes | Pavan Vignesh | Completed | Low |  | Ready for deployment
F-02 | Authentication | User register, login, JWT and role-based access controls | Tharun | Completed | High |  | Verified auth layers
F-03 | Parent Dashboard | Command center for child metrics, sleep, active logs | Pavan Vignesh | Completed | High |  | Responsive layout complete
F-04 | Doctor Dashboard | Pediatric dashboard for patients grid, notes and charts | Pavan Vignesh | Completed | High |  | Merged details view
F-05 | Child Profile Management | Creation and maintenance of multiple child records | Tharun | Completed | Medium |  | Validated with Zod schemas
F-06 | Meal Logging | 6 slot meal logging journal with portions and image upload | Pavan Krishna | Completed | High |  | Linked to local food db
F-07 | Nutrition Analysis | RDA target comparison and calorie/protein gap tracker | Pavan Krishna | Completed | High |  | Deterministic gap analysis
F-08 | AI Nutrition Assistant | Parents conversational RAG guide with citation viewer | Abhiram | Completed | High |  | RAG and planning active
F-09 | Food Buddy | Gamified kids chatbot with story prompt filters and XP | Abhiram | Completed | Medium |  | Verified kid story filters
F-10 | Doctor Access System | Secure restricted or full permission doctor connection | Tharun | Completed | High |  | Validated with handshake logic
F-11 | Growth Tracking | Logs height, weight, BMI risk status over time | Pavan Krishna | Completed | Medium |  | Computes BMI percentiles
F-12 | RAG Pipeline | BM25 and FAISS hybrid vector search with reranker | Dinesh Veera | Completed | High |  | Guideline textbooks loaded
F-13 | Privacy Mode | Local Ollama offline model router toggle | Abhiram | Review | Medium |  | Integrating static fallback
F-14 | Deployment | MongoDB Atlas, Prometheus telemetry and compose setups | Tharun | Completed | High |  | Staging containers running

## User Stories
NutriBite User Stories
Story ID | Feature | User Story | Assigned To | Status | Reviewer | Comments
US-01 | Landing Page | As a prospective user, I want to view a visually engaging landing page, so that I can understand NutriBite's clinical and gamified features. | Pavan Vignesh | Completed | Abhiram | Visual layout verified
US-02 | Authentication | As a parent or doctor, I want secure registration and login, so that my child's medical and dietary data is protected. | Tharun | Completed | Abhiram | Auth tests passed
US-03 | Parent Dashboard | As a parent, I want to see a central dashboard with quick logging tools and water intake counters, so that I can easily monitor my child's daily habits. | Pavan Vignesh | Completed | Tharun | Linked to stats API
US-04 | Doctor Dashboard | As a pediatrician, I want a unified patient list and growth graphs, so that I can review real-time meal diaries and growth histories. | Pavan Vignesh | Completed | Tharun | Grid layouts complete
US-05 | Child Profile Management | As a parent, I want to create separate child profiles with dietary preferences and custom avatars, so that I can manage each child's health goals individually. | Tharun | Completed | Pavan Krishna | DB schema tested
US-06 | Meal Logging | As a parent, I want to log breakfast, lunch, dinner, snacks, and upload meal photos, so that I have a complete dietary history for analysis. | Pavan Krishna | Completed | Abhiram | Form validation tested
US-07 | Nutrition Analysis | As a parent, I want to view auto-calculated macro totals and RDA gaps, so that I can identify dietary deficiencies like iron or calcium. | Pavan Krishna | Completed | Dinesh Veera | Target comparisons verified
US-08 | AI Nutrition Assistant | As a parent, I want to chat with an AI assistant that references NIN/ICMR guidelines, so that I can get reliable, safe pediatric advice. | Abhiram | Completed | Dinesh Veera | Citations verified
US-09 | Food Buddy | As a child, I want to chat with a superhero mascot, earn XP, and unlock badges for eating healthy, so that eating well is fun. | Abhiram | Completed | Pavan Vignesh | Kids mode flow validated
US-10 | Doctor Access System | As a parent, I want to approve or deny access requests from specific doctors, so that I control who sees my child's clinical records. | Tharun | Completed | Abhiram | Two-way handshake verified
US-11 | Growth Tracking | As a parent, I want to record height and weight logs to calculate BMI, so that I can monitor my child's physical development. | Pavan Krishna | Completed | Tharun | Growth velocity calculated
US-12 | RAG Pipeline | As a developer, I want hybrid keyword/semantic retrieval, so that chat answers are clinically correct. | Dinesh Veera | Completed | Abhiram | Retrieval MRR is above 0.85
US-13 | Privacy Mode | As a parent, I want local offline inference routing, so that child PII is not sent to external cloud APIs. | Abhiram | Review | Tharun | Model router works offline
US-14 | Deployment | As a developer, I want a containerized deployment with metrics, so that operations are stable and observable. | Tharun | Completed | Dinesh Veera | Telemetry dashboards running

## Tasks
NutriBite Detailed Task Registry
Task ID | Feature | Task Name | Assigned To | Reviewed By | Status | Due Date | Comments
T-001 | Landing Page | Create Hero Section | Pavan Vignesh | Abhiram | Completed | 2026-04-15 | Responsive layout complete
T-002 | Landing Page | Create About Section | Pavan Vignesh | Abhiram | Completed | 2026-04-16 | Standard copy written
T-003 | Landing Page | Create Features Section | Pavan Vignesh | Abhiram | Completed | 2026-04-17 | Icons added
T-004 | Landing Page | Create Contact Section | Pavan Vignesh | Abhiram | Completed | 2026-04-18 | Feedback form integrated
T-005 | Landing Page | Responsive Design | Pavan Vignesh | Abhiram | Completed | 2026-04-20 | Viewport tested on mobile
T-006 | Authentication | Login UI | Pavan Vignesh | Tharun | Completed | 2026-04-22 | Auth forms structured
T-007 | Authentication | Registration UI | Pavan Vignesh | Tharun | Completed | 2026-04-23 | Role check dropdown added
T-008 | Authentication | JWT Authentication | Tharun | Abhiram | Completed | 2026-04-25 | Cookie parser configuration
T-009 | Authentication | Role Based Access | Tharun | Abhiram | Completed | 2026-04-27 | Express route guarding
T-010 | Parent Dashboard | Child Selection Widget | Pavan Vignesh | Tharun | Completed | 2026-04-29 | Dynamic dropdown list
T-011 | Parent Dashboard | Activity Level Widget | Pavan Vignesh | Tharun | Completed | 2026-04-30 | Active settings tags
T-012 | Parent Dashboard | Caloric Summary UI | Pavan Vignesh | Pavan Krishna | Completed | 2026-05-02 | Circular charts embedded
T-013 | Parent Dashboard | Water Logger Stats Card | Pavan Krishna | Tharun | Completed | 2026-05-04 | Quick +250ml logging
T-014 | Doctor Dashboard | Patients Grid | Pavan Vignesh | Tharun | Completed | 2026-05-06 | Patient list layout complete
T-015 | Doctor Dashboard | Pending Requests Mailbox | Pavan Vignesh | Tharun | Completed | 2026-05-07 | Approval controls
T-016 | Doctor Dashboard | Diagnostic Notes | Tharun | Abhiram | Completed | 2026-05-09 | Notes storage controller
T-017 | Doctor Dashboard | Recharts Growth Curves | Pavan Vignesh | Pavan Krishna | Completed | 2026-05-11 | BMI data plotting
T-018 | Child Profile Management | Create Profile Form | Pavan Vignesh | Tharun | Completed | 2026-05-13 | React state hooks configured
T-019 | Child Profile Management | Demographics | Tharun | Pavan Krishna | Completed | 2026-05-14 | Mongoose schema defined
T-020 | Child Profile Management | Animal Avatar Selector | Pavan Vignesh | Tharun | Completed | 2026-05-16 | Vibrant graphics selection
T-021 | Child Profile Management | Health Conditions List | Tharun | Pavan Krishna | Completed | 2026-05-17 | Allergy text array
T-022 | Meal Logging | Daily Slots | Pavan Krishna | Abhiram | Completed | 2026-05-19 | 6 distinct slot containers
T-023 | Meal Logging | Portion Sliders | Pavan Vignesh | Pavan Krishna | Completed | 2026-05-20 | Vite UI sliders
T-024 | Meal Logging | Photo Upload API | Tharun | Abhiram | Completed | 2026-05-22 | Multer file storage routes
T-025 | Meal Logging | Delete Food Item | Pavan Krishna | Tharun | Completed | 2026-05-23 | Route delete handlers tested
T-026 | Nutrition Analysis | RDA Target Calculation | Pavan Krishna | Abhiram | Completed | 2026-05-25 | WHO reference lookup tables
T-027 | Nutrition Analysis | Gap Detection Algorithm | Pavan Krishna | Dinesh Veera | Completed | 2026-05-26 | Nutrient deficiency checkers
T-028 | Nutrition Analysis | Dynamic Food Recommendations | Abhiram | Dinesh Veera | Completed | 2026-05-28 | Recommender system rules
T-029 | AI Nutrition Assistant | Parent Chat Interface | Pavan Vignesh | Abhiram | Completed | 2026-05-30 | Streaming text container
T-030 | AI Nutrition Assistant | Clinical View Toggle | Pavan Vignesh | Abhiram | Completed | 2026-06-01 | Text splitting details
T-031 | AI Nutrition Assistant | Dynamic Query Citations | Abhiram | Dinesh Veera | Completed | 2026-06-02 | Citation source mapping
T-032 | Food Buddy | Avatar Custom Framing | Pavan Vignesh | Abhiram | Completed | 2026-06-04 | Super-hero kids layout theme
T-033 | Food Buddy | Fun Chat Story Prompt Rules | Abhiram | Dinesh Veera | Completed | 2026-06-05 | Interactive kids character logic
T-034 | Food Buddy | XP Tracker | Pavan Krishna | Tharun | Completed | 2026-06-07 | Completed logs reward triggers
T-035 | Food Buddy | Unlocked Badges Drawer | Pavan Vignesh | Tharun | Completed | 2026-06-08 | Badge grid animations
T-036 | Doctor Access System | Doctor Access Request Link | Tharun | Abhiram | Completed | 2026-06-10 | Email access invitation system
T-037 | Doctor Access System | Parent Access List | Tharun | Abhiram | Completed | 2026-06-11 | Access listing controllers
T-038 | Doctor Access System | Restricted/Full View Approval Logic | Tharun | Abhiram | Completed | 2026-06-12 | Permissions checks middleware
T-039 | Doctor Access System | Revoke Access | Tharun | Abhiram | Completed | 2026-06-13 | Delete access mapping records
T-040 | Growth Tracking | Height/Weight Logs | Pavan Krishna | Tharun | Completed | 2026-06-14 | Height-weight form fields
T-041 | Growth Tracking | BMI Category Status | Pavan Krishna | Tharun | Completed | 2026-06-15 | Calculates WHO risk statuses
T-042 | Growth Tracking | Longitudinal Growth Database Storage | Tharun | Pavan Krishna | Completed | 2026-06-16 | GrowthRecord schemas indices
T-043 | RAG Pipeline | BM25 Keyword Matching | Dinesh Veera | Abhiram | Completed | 2026-05-15 | Okapi BM25 indices created
T-044 | RAG Pipeline | FAISS Dense Search Vector Indexing | Dinesh Veera | Abhiram | Completed | 2026-05-16 | SentenceTransformers indexing
T-045 | RAG Pipeline | Cross-Encoder Reranker | Dinesh Veera | Abhiram | Completed | 2026-05-18 | ms-marco-MiniLM model scoring
T-046 | RAG Pipeline | Textbook Ingestion | Dinesh Veera | Abhiram | Completed | 2026-05-20 | Parsed PDF pages into clean text
T-047 | Privacy Mode | Offline Toggle | Pavan Vignesh | Tharun | Completed | 2026-06-10 | Dashboard layout toggle button
T-048 | Privacy Mode | Local Ollama Router | Abhiram | Dinesh Veera | Completed | 2026-06-11 | Verifies local tags ping endpoint
T-049 | Privacy Mode | Local Static Fallback Generator | Abhiram | Dinesh Veera | In Progress | 2026-06-20 | Developing backup response template
T-050 | Deployment | MongoDB Atlas Configuration | Tharun | Pavan Krishna | Completed | 2026-06-14 | Cluster setup and security limits
T-051 | Deployment | NextJS Production Container | Tharun | Pavan Krishna | Completed | 2026-06-15 | Multi-stage build completed
T-052 | Deployment | Prometheus Metrics Scraper | Dinesh Veera | Abhiram | Completed | 2026-06-16 | Instruments AI service metrics
T-053 | Deployment | Docker-Compose Orchestration | Tharun | Pavan Krishna | In Progress | 2026-06-21 | Container bridge configuration

## Team Contributions
NutriBite Team Contribution Tracker
Member | Role | Features Owned | Tasks Assigned | Tasks Completed | Contribution % | Comments
Abhiram | AI Engineer & Feature Lead |  |  |  |  | LLM Integration, Ollama Router, Story prompts
Tharun | Backend & Database Engineer |  |  |  |  | Auth backend, MongoDB database schemas, express server
Dinesh Veera | RAG Engineer |  |  |  |  | FAISS indexes, BM25 retriever, Cross-Encoder reranker
Pavan Krishna | Data Engineer & Backend Developer |  |  |  |  | Indian foods dataset, sleep log logic, BMI calculations
Pavan Vignesh | Frontend & UI/UX Engineer |  |  |  |  | Web UI dashboards, Recharts velocity lines, animations
Total